## Sheet1
focus | task | ...pre | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | post…
project management | document progress and next steps on the project blog
discuss and confirm next-phase action plan with mentor
gather relevant library methods
Build prototype models, implementing main algorithm | elevation
force
electromagnetism
distance
sound
sustainability and testing | field prototype to peers
establish limits and extent of consumer use
test portability
Evaluation and revision | write documentation
algorithm revision
bug fixing
User engagement and experience | revise proposed wireframes
augment user interface
polish and revise user interface
Final report and dissemination | fulfill Google's commit and report requirements
detail next dev steps for open source community
release to app store and github